## Slide 1: Noida Institute of Engineering and Technology, Greater Noida
Project Monitoring and Control
Earned Value Analysis
Project Termination
Tarun Maheshwari
Assistant Professor
Department of PGDM
Unit: V
Project Management
B.Tech VII Semester

## Slide 2
Index
S. No. | Content
1. | Name of Subject with code, Course and Subject Teacher
2. | Brief Introduction of Faculty member with Photograph
3. | Evaluation Scheme
4. | Syllabus
5. | Branch wise Application
6. | Course Objective(s)
7. | Course Outcome(s)
8. | Program Outcomes (PSOs)
9. | Cos and POs Mapping

## Slide 3
Index
S. No. | Content
10. | Program Specific Outcomes (PSOs)
11. | Cos and PSOs Mapping
12. | Program Educational Objectives (PEOs)
13. | Result Analysis
14. | End Semester Question paper Templates
15. | Prequisite/Recap
16. | Brief Indtroduction about the Subject with Videos
17. | Unit Contents
18. | Unit Objectives
19. | Topic Objectives/Topic Outcome

## Slide 4
Index
S. No. | Content
20. | Lecture related to topic
21. | Daily Quiz
22. | Weekly Assignment
23. | Topic Links
24. | MCQs
25. | Glossary Questions
26. | Old question papers
27. | Expected Questions
28. | Recap of unit

## Slide 5
Faculty Name: Tarun Maheshwari
Designation: Assistant Professor
Department: PGDM
Email ID: tarun.maheshwari@niet.co.in
Qualification: MBA, PG Diploma In Traning & Development
Specialization: Human Resource
Teaching Area: HR
Total Experience: 11 years
Faculty Profile

## Slide 6
Evaluation Scheme

## Slide 7
Syllabus

## Slide 8
Handling projects.
Evaluating & Monitoring Project Process
Taking necessary and corrective action.
Branch Wise Application

## Slide 9
To empower the students to get insights of basic concepts on project management.
To create awareness on the roles and responsibilities of project manager.
To build the confident among the students to take up any kind of projects.
To sharpen the planning, scheduling and controlling skills of the students with respect to individual projects.
To understand the perspectives in which optimum decisions are to be taken in case of risks with planned activities in project.
Course Objectives

## Slide 10
Course Outcome

## Slide 11
1. Apply knowledge of management theories and practices to solve business problems.
2. Foster analytical and critical thinking abilities for data-based decision making.
3. Ability to develop value based leadership ability.
4. Ability to understand, analyze and communicate global, economic, legal and ethical aspects of business.
5. Ability to lead themselves and others in the achievement of organizational goals, contributing effectively to a team environment.
Program Outcomes

## Slide 12
CO-PO and PSO Mapping
S No | CO/PO | PO1 | PO2 | PO3 | PO4 | PO5 | PO6
1 | CO1 |  | 3 |  | 2 |  | 
2 | CO2 |  |  | 3 |  |  | 2
3 | CO3 |  | 3 |  |  |  | 
4 | CO4 |  |  | 1 |  | 3 | 
5 | CO 5 | 1 | 2 |  |  |  | 
Program Specific Outcomes | Course Outcomes |  |  |  |  | 
 | 1 | 2 | 3 | 4 | 5 | 
1 |  | 3 |  | 1 |  | 
2 | 1 |  | 1 |  | 2 | 
3 | 1 |  | 2 |  |  | 
*1=High, *2=Medium, *3=Low

## Slide 13
PEO 1: Graduates of the Management program will have conceptual knowledge, to adapt to the rapidly changing environment, learn new skills and demonstrate application of management principles in a professional work setting.
PEO 2: Graduates will apply appropriate tools for decision making required for solving complex managerial problems in the local or global context.
PEO 3: Graduates of the Management program will exhibit integrity, social responsibility and teamwork.
PEO 4: Graduates will exhibit ethics, communication skills, leadership qualities and entrepreneurial mindset using creativity and innovation.
Program Educational Objective

## Slide 14
Subject is first time introduced under the autonomous status. This would be the first result of the course.
Result Analysis

## Slide 15
End Semester Question Paper Template

## Slide 16
End Semester Question Paper Template

## Slide 17
Objective of this unit are:
To make the students learn about project and project management.
To make to students understand the project management process.
To make the students know about the project life cycle.
Objective of Unit

## Slide 18
Unit-1:
Monitoring the project – Control cycle – Project control – Designing the control system .
Evaluation of project: Milestone Analysis and Tracking Gantt chart. Earned Value Analysis (EVA): Planned Value (PV), Earned Value (EV), Cost Variance (CV), Schedule Variance (SV), Cost performance Index (CPI), Schedule performance Index (SPI) – Project auditing –
Project termination: Types of Terminations, Project Termination Process. Case Study
Content of Unit

## Slide 19
Prerequisites for this session are:
General understanding of project management.
Moderate analytical skills.
Recap:
Project Scheduling and Network Analysis:
Project Network Design:
Prerequisites and Topic wise Recap

## Slide 20
Topic & CO Mapping
S No | Topic | CO | Level
1 | Project Monitoring and Control | CO 5 | 2
2 | Earned Value Analysis (EVA): | CO 4 | 2
3 | Project Termination | CO 5 | 1

## Slide 21
To understand the Project Monitoring and Control.
To perform the Earned Value Analysis and learning about its components.
To understand and learning to execute Project Termination.
Session/ Topic Objectives

## Slide 22
Project Monitoring & Control
According to the Project Management Body of Knowledge (PMBOK),
“The Monitoring and Control Process Group consists of those processes performed to observe project execution so that potential problems can be identified in a timely manner and corrective action can be taken, when necessary, to control the execution of the project.”

## Slide 23
Monitoring and Control Processes
1. Monitoring and Controlling Project Work
2. Integrated Change Control
3. Scope Verification
4. Scope Control
5. Schedule Control
6. Cost Control
7. Performing Quality Control
8. Managing the Project Team
9. Performance Reporting
10. Managing Stakeholders

## Slide 24
Project monitoring & Control Cycle

## Slide 25
PROJECT MANAGEMENT INFORMATION SYSTEM (PMIS)

## Slide 26
PMIS

## Slide 27
Components of a PMIS
Scheduling
Estimating
Resources
Project documents and data
Portals and dashboards
Collaborative work management tools
Social media
Project control

## Slide 28
Milestone Analysis
Milestone
Milestones are tools used in project management to mark specific points along a project timeline. These points may signal anchors such as a project start and end date, or a need for external review or input and budget checks.
In many instances, milestones do not impact project duration. Instead, they focus on major progress points that must be reached to achieve success.

## Slide 29
Milestone Analysis: Steps
Set the milestones
Reassess after each milestone
Track your progress
Read the nuances

## Slide 30
Tracking Gantt Chart

## Slide 31
Tracking Gantt Chart
Layout options - options for drawing the links between tasks, date format, bar height, etc.
Bar styles - the styles for drawing the bars and displaying information about bars in the particular view
Text styles - the font styles for the various texts in the view
Bar formatting - the specific formatting of a particular bar in the chart, in case the project manager intentionally changed the format to make the task stand-out from the others by its visual presentation

## Slide 32
Tracking Gantt Chart
Row, Column, and Cell Font formatting - the specific font formatting of a particular row, column, or cell in the sheet portion of the view, in case the project manager intentionally applied a different format to highlight the particular task, field, or value
Progress Lines formatting - the progress lines activated for the view and formatting options related to them

## Slide 33
Tracking Gantt Chart
Timescale formatting - the formatting of the different timescale tiers, as well as the calendar and presentation of the working and non-working days .
Gridlines formatting - the formatting of the different gridlines for the sheet and chart portions of the view.
Drawings - the different drawings and text boxes placed on the chart by the project manager, in order to place additional information for the tasks or emphasize a certain phase in the plan.

## Slide 34
Topic | CO | Level
Earned Value Analysis (EVA) | CO 4 | 2

## Slide 35
Objective:
To understand and analyze the earned value of project.
Outcome:
Student would be able to identify and analyze the earned value of project for optimizing value and cost.
Topic Objectives & Outcome

## Slide 36
Recap
Project Monitoring
Project Control
PMIS

## Slide 37
Earned Value Analysis
The earned value analysis is a project controlling procedure that, along with the planned and actual costs, includes the earned value.
Through this the project’s cost efficiency and time efficiency can be calculated.

## Slide 38
Earned Value
Oftentimes the term “earned value” is defined as the “budgeted cost of work performed” or BCWP.
This budgeted cost of work performed measure enables the project manager to compute performance indices or burn rates for cost and schedule performance, which provides information on how well the project is doing or performing relative to its original plans.

## Slide 39
EVM Foundational Concepts
Earned Value Management Systems allow the project manager to answer the following three questions, as they relate to the project:
Where have we been?
Where are we now?
Where are we going?

## Slide 40
Planned Value (PV)
Planned Value describes how far along project work is supposed to be at any given point in the project schedule and cost estimate. Cost and Schedule baseline refers to the physical work scheduled and the approved budget to accomplish the scheduled work.
Together, they result in an important value: Planned Value (PV). PV can be looked at in two ways: cumulative and current.

## Slide 41
Planned Value (PV): Cumulative & Current
Cumulative PV is the sum of the approved budget for activities scheduled to be performed to date.
Current PV is the approved budget for activities scheduled to be performed during a given period. This period could represent days, weeks, months, etc.

## Slide 42
Earned Value
EV is the quantification of the “worth” of the work done to date.
In other words, EV tells you, in physical terms, what the project has accomplished.

## Slide 43
Earned Value: Cumulative & Current
Cumulative EV is the sum of the budget for the activities accomplished to date.
Current EV is the sum of the budget for the activities accomplished in a given period. Earned Value is also called Budgeted Cost of Work Performed (BCWP).

## Slide 44
Variance Analysis
A quantifiable deviation, departure, or divergence away from a known baseline or expected value.
There are two basic expressions of variance, schedule variance and cost variance.

## Slide 45
Schedule Variance
Schedule Variance status does indicate the Monetary value difference between work that is ahead or behind the plan and reflects a given measurement method.
The formula utilized to express schedule variance is project earned value minus the project planned value as of the date of examination.
(SV = EV – PV)

## Slide 46
Schedule Variance
If the variance is equal to 0, the project is on schedule.
If a negative variance is determined, the project is behind schedule.
If the variance is positive the project is ahead of schedule.

## Slide 47
Cost Variance
The cost variance is defined as the difference between earned value and actual costs.
(CV = EV – AC)

## Slide 48
Graphic Representation

## Slide 49
Performance Indexes
Another analysis that can be done by using EVMS is that of Performance or establishing the project’s burn rate.
Two examination of performance are available to the project manager:
Schedule Performance Index (SPI)
Cost Performance Index (CPI).

## Slide 50
Schedule Performance Index (SPI)
A measure of schedule efficiency on a project. It is the ratio of earned value (EV) to planned value (PV).
The SPI is equal to earned value divided by planned value.
SPI = EV/PV
An SPI equal to or greater than one indicates a favorable condition and a value of less than one indicates an unfavorable condition.

## Slide 51
Cost Performance Index (CPI)
A measure of cost efficiency on a project. It is the ratio of earned value (EV) to actual costs (AC).
The CPI is equal to the earned value divided by the actual costs.
CPI = EV/AC.
A CPI equal to or greater than one indicates a favorable condition and a value of less than one indicates an unfavorable condition.

## Slide 52
Topic | CO | Level
Project Termination | CO 5 | 1

## Slide 53
Objective:
To learn and understand the process of project termination.
Outcome:
Student would be able to apply step wise step appreach to terminate the projects.
Topic Objectives & Outcome

## Slide 54
Recap
Earned Value Analysis
Variance
SPI & CPI

## Slide 55
Project Termination
Project termination (or close-out) is the last stage of managing the project, and occurs after the implementation phase has ended.

## Slide 56
Types of Project Termination

## Slide 57
Most Common Reasons Projects Terminate

## Slide 58
Summary
Milestones are tools used in project management to mark specific points along a project timeline.
These points may signal anchors such as a project start and end date, or a need for external review or input and budget checks.
A measure of cost efficiency on a project. It is the ratio of earned value (EV) to actual costs (AC).
The CPI is equal to the earned value divided by the actual costs.

## Slide 59
https://www.youtube.com/watch?v=lfIX8VwZpPE
https://www.youtube.com/watch?v=QTL0NU_S2Mc
https://www.youtube.com/watch?v=rAJYAgTBXEY
https://www.youtube.com/watch?v=mYUIMsc6Niw
Youtube Links

## Slide 60
Q1. EVA stands for.
Earned value analysis
Early value analysis
Exposure value analysis
Explicit value analysis
Q2. PV stands for.
Projected value
Planned value
Peculiar value
None of the above
Daily Quiz

## Slide 61
Q3. EV stands for.
Explicit value
Exposure value
Earned value
Expected value
Q4. In project monitoring CV stands for.
Cumulative variance
Cumulative value
Cost variance
None of the above
Daily Quiz

## Slide 62
Q5. In project monitoring SV stands for.
Standard value
Schedule variance
Schedule value
Standard variance
Q6. In project monitoring and control SPI stands for.
Supplementary performance index
Schedule performance index
Social performance index
Substitute performance index
Daily Quiz

## Slide 63
Q1. Describe the project monitoring and control cycle.
Q2. Discuss the Project Management Information System.
Q3. Describe the project termination and its process in detail.
Q4. Discuss the Earned Value Analysis and calculation of its components.
Weekly Assignment

## Slide 64
Q1. Who will be aware that for all projects, final technical and financial reports
Principal Investigator
Foremen
Supervisor
Clerk
Q2. Why projects are terminated?
Force majeure (e.g. earthquake, flooding, etc.)
Necessary conditions disappear
Lack of management support
All of the above
MCQ s

## Slide 65
Q3. We generally extol the value and virtue of time as a
Critical parameter
Compact parameter
Complex parameter
None of the above
Q4. Projects are the means of_________organizational strategy
Implementing
Making
Terminating
None of the above
MCQ s

## Slide 66
Q5. Which of the following is an incorrect activity for the configuration management of a software system? A. Internship management B. Change management C. Version management D. System management
Q6. Quality planning is the process of developing a quality plan applicable for.
Team
Project
Customers
project manager
MCQ s

## Slide 67
Part of Question Bank.
Yet to be prepared for IV sem Batch 2020-22
Glossary Questions

## Slide 68
Old Question Papers

## Slide 69
Old Question Papers

## Slide 70
Old Question Papers

## Slide 71
Old Question Papers

## Slide 72
Q1. Discuss the project monitoring and control process.
Q2. Elaborate the project monitoring and control cycle.
Q3. Elaborate the earned value analysis with its components.
Q4. Explain the project termination and various types of terminations
Expected Questions for University Exam

## Slide 73
The Monitoring and Control Process Group consists of those processes performed to observe project execution so that potential problems can be identified in a timely manner and corrective action can be taken, when necessary, to control the execution of the project.”
The earned value analysis is a project controlling procedure that, along with the planned and actual costs, includes the earned value.
Summary

## Slide 74
References
Books:
1. Project Management – Achieving Competitive Advantage: Jeffrey K. Pinto (Pearson)
2. Project Management- A Managerial Approach: Jack R. Meredith Broyhill Samuel J. Mantel, Jr (John Wiley & Sons)
4. Project- Preparation, Appraisal, Budgeting and Implementation: Chandra Prasanna - (TMH)
Web-links:
https://www.projectplan365.com/articles/tracking-gantt/
https://www.google.com/search?q=project+termination+process+in+project+management&sxsrf=ALeKk00XHUBeTKGmy4P_46lOCdOVVwx4qQ:1592294685524&source=lnms&tbm=isch&sa=X&ved=2ahUKEwjtwu7474XqAhUTT30KHe6sCzsQ_AUoAXoECA0QAw&biw=1366&bih=625#imgrc=M3vpROgkXZRujM
http://www.technologyuk.net/computing/software-development/project-management/project-termination.shtml#:~:text=Project%20termination%20(or%20close%2Dout,handed%20over%20to%20the%20client.

## Slide 75
Thank You